## Contents
Project Management Workbook
<Your Project Name>
Prepared By: | <Project Manager Name>
Organization: | <Org Name> |  | "Energy and persistence conquer all things." - Benjamin Franklin
Process | 8 Best Practices | ID# | "Thinking Tools" Link | Approved
Start | Select | 1 | Initial Project Definition | 2022-02-22
| Select | 2 | Business Case
| Scope | 3 | Project Agreement
Do | Plan+Schedule | 4 | Management Plan
| Plan+Schedule | 5 | Deliverables & Definitions
| Plan+Schedule | 6 | Status Report
| Plan+Schedule | 7 | Change Log
| Plan+Schedule | 8 | Schedule
| Resource | 9 | Resource Plan & Budget
| Resource | 10 | Organization & RACI Charts
| Quality | 11 | Quality Tracker
| Stakeholders | 12 | Stakeholder Analysis & Management Matrix (SAMM) & Communication Plan
| Stakeholders | 13 | Kick Off Agenda
| Stakeholders | 14 | Decisions & Agreements
| Risk | 15 | Rolling Action & Issue Log (RAIL)
| Risk | 16 | Risk Analysis and Response Worksheet
Deliver | Transition | 17 | Lessons Learned
| Transition | 18 | Complete Transition & Close the Project
About this Document:
Purpose: | This workbook enables project managers to successfully navigate a small to medium-sized project through our simple, practical, results-oriented Start -> Do -> Deliver project management process. Coupled with a scheduling tool, your organization knowledge, leadership and communication skills, you will surely achieve success! Click on the links above to go directly to what you need and enjoy the journey!
Help: | If you have any questions regarding the content, need further assistance, and/or would like additional information regarding Project Management training please contact your manager, human resources or:
| Dawn Mahan, PMP |  | DMahan@PMOtraining.com

## PjctDef
Initial Project Definition
Table of Contents
1 | About this Document
2 | Overview of the Business/IT Solution Planning Process
3 | Step 1: Define the Problem or Opportunity
4 | Project Manager Checklist
5 | Problem Definition
6 | Project Value, Benefits, and Cost
7 | Priorities & Options
8 | Stakeholders & Steering Team
9 | Step 2: Deliberate Goals and Objectives |  | 5 Delivery Objectives - FORCE RANK … 1. TIME 2. SCOPE (things) 3. QUALITY 4. STAKEHOLDER SAT 5. COST/RESOURCES (Effort Hours) [Ops/Gov/Policy]
10 | Project Manager Checklist
11 | Goals
12 | Objectives
13 | Step 3: Generate Alternatives
14 | Project Manager Checklist
15 | Team Guidelines
16 | Analysis Considerations
17 | Alternatives
18 | Step 4: Determine Solution(s) and Approach
19 | Project Manager Checklist
About this Document
The purpose of this document is to support the Project Manager (PM) and requesting Organization to progress from an identified problem or opportunity to a high-level solution. Upon completion of this document, the Project Manager should be able to prepare an inital Project Agreement for review and approval.
This document should be prepared by the PM with input from the requesting organization. The requesting organization retains full ownership and responsibility for the content of this document. However, the project manager is responsible for maintaining the document.
Overview of the Initial Project Definition Process
The process to initially define the project, consists of four steps, as follows:
1) Define the Problem or Opportunity
2) Deliberate Goals and Objectives
3) Generate Alternatives
4) Determine Solution(s) and Approach
The remainder of this workbook will guide the PM and the initial team through completion of these four steps.
Step 1: Define the Problem or Opportunity
The first step is to clearly identify the problem or opportunity.
Project Manager Guidelines
Before the meeting:
Prepare for a first meeting with the Project Sponsor, including drafting the meeting objectives and agenda
Request and schedule a meeting with the Project Sponsor, sending along the draft objectives and agenda
Review guidelines below and fill in as many of the answers as possible
During the meeting:
If haven’t already, review Roles & Responsibilities with the Project Sponsor
Define the problem or opportunity, using the questions in this section as a guide
Document the answers
Discuss what should be done after this meeting (e.g., review output, goal deliberation meeting - who should attend and when)
After the meeting:
Distribute meeting output
Receive agreement from Project Sponsor that the documented answers were captured completely and accurately
Schedule Goal Deliberation meeting(s) (include Project Sponsor, Project Requester, and a limited group that can speak for the larger list of stakeholders)
The following questions should help you to understand the problem and/or opportunity the sponsoring organization wishes to address (fill in the answers as appropriate).
Note: Focus on clearly understanding the real problem and/or opportunity. Often the requesting organization has already generated ideas about their desired solution. Possible desired solutions should be noted but it is best to keep an open mind about solutions until the problem/opportunity and delivery objectives (e.g., cost, schedule, etc.) are clearly defined.
Problem Definition/Strategic Fit
1) What primary problem is this project being initiated to resolve (and/or opportunity it needs to exploit)?
2) What vision/strategy element does this support?
3) What business strategy does it support? How is it supporting it?
4) Are there any specific target goals driving this initiative? If so, where did these targets originate and how will they be measured?
5) Is this project part of or related to a larger business initiative? If so, what is that initiative?
6) What are the connection points to that initiative?
7) Is the need driven by an external customer or governmental organization? If so, what are the drivers?
8) What is the scope of the problem or opportunity; site, regional, global?
Project Value, Benefits, and Cost
9) What is the value of solving this problem or exploiting the opportunity? What is the business committing to for benefits realization from the project? Quantify where possible.
10) What other benefit(s), aside from resolution of the primary problem or opportunity, will be achieved? What is the value of this benefit?
11) What are the target returns on investment for this initiative?
12) What is the cost of not doing the solution, or being deficient in the desired functionality? Quantify where possible.
Priorities & Options
13) What options have been considered for the solution, if any? If there is a favored option at this point, describe why it is the most attractive.
14) Are there any hard constraints around cost or time (i.e. an investment target or cap, and/or statutory or critical requirements for completion date), or special time sensitivities we need to be aware of?
15) What are the delivery objectives in priority order? Cost/resources, scope, schedule, quality and stakeholder satisfaction? Why?
16) What is the priority of this project versus others? For the sponsor? For the organization?
17) Are there any incentives or penalties for early or late completion of the project? If so, how much (per month, year)?
Stakeholders & Project Leadership
18) Who are all the internal and external stakeholders that may be impacted (positively or negatively) if this problem or opportunity is addressed?
19) Out of this list of stakeholders, who should be consulted as part of goal deliberation? Out of that list, who should be in the initial goal deliberation session (speaking for the broader group), and who can be consulted afterward or informed via email?
20) What direct feedback do we already have from internal or external stakeholders, regarding the problem or opportunity and any desired solutions?
21) What is the expected change impact of the project? For example, will any stakeholders have to do anything as a result of this project (i.e. invest time, money, change work processes, install equipment, etc.)?
22) Is there any additional value to internal or external stakeholders beyond what was already mentioned (i.e. can they use the solution for other purposes)?
23) Who are the most influential and interested executives/leaders? What is the right way to involve them to ensure project success (e.g., provide guidance, remove barriers, provide resources, lend support)?
Step 2: Deliberate Goals and Objectives
Note: While the goal and objective deliberation process may be less formal for smaller projects, the same thinking should be done and the sponsor and key stakeholders must be involved similarly.
Project Manager Guidelines
Before the Goals meeting:
Gather any other related information, as appropriate (i.e. current as-is state, current processes, system background, key players, related projects, etc.)
Consider the size and complexity of the project and decide how many meetings goal deliberation should require (and whether goals and objectives can be covered in one meeting). Tailor the steps below accordingly.
Prepare for the meeting by:
- Create initial draft of high-level Goals based on information gathered in Step 1
- Prepare and distribute draft meeting objectives and agenda along with background information (e.g., definitions and draft "goals")
During the Goals meeting:
Communicate/discuss problem as identified in Step 1
Discuss & modify draft goals
Prioritize the goals, understanding the reasons for the priority order
Determine next steps (e.g., reviewing goals with a broader audience)
After the Goals meeting:
Update this document with agreed-upon, prioritized goals
Send/review goals with broader audience to receive feedback (up to two rounds), as required
Finalize goals (may require meeting with the original group to
Before the Objectives meeting:
Schedule meeting to discuss Objectives
Prepare for the meeting by:
- Creating an agenda
- Creating initial draft of objectives (team will modify during meeting)
- Reviewing SMART guidelines for writing objectives
During the Objectives meeting:
Communicate (and modify, as appropriate) draft Objectives
After the Objectives meeting:
Send/review goals and objectives to appropriate audience and receive feedback (up to two rounds)
Finalize objectives
Acquire the team to be involved in Step 3: Generate Alternatives (see Team Guidelines)
Schedule the meeting for Step 3: Generate Alternatives
Goals
Based on the problem or opportunity that has been identified, list the primary goals of this project, stated as general ends toward which efforts can be directed (not how to get there). These should be broad statements that describe desired outcomes, and are generally not quantified. However, they should keep the scope in mind and be generally measurable. Objectives will be reviewed later, which will detail specific, measurable targets toward reaching these goals.
Examples of well-written and poorly written goals are:
- Poor: To provide good roads (too general)
- Better: To provide road surfaces that ensure a smooth and comfortable ride for people and goods traveling in the state by automobile.
- Poor: To continue to serve our customers (not challenging and doesn’t clarify the mission)
- Better: To provide health benefits plans that are affordable to both our members and state agencies
- Poor: To reduce by 15% the amount of contaminants in our drinking water by the year 2006 (time-bound and too specific – this is an objective, not a goal)
- Better: To ensure safe drinking water quality for all citizens of our state and those served by public water supply systems.
Note that, in the examples above, the well-written goals were broad, but gave a sense of scope limitations and were specific enough to act as drivers for developing specific objectives and solutions.
List the goals for this project in a bulleted list format:
Objectives
Once the goals have been deliberated, prioritized, and agreed-upon, the next step is to define the specific objectives. Objectives should be SMART (Specific, Measurable, Achievable, Realistic, and Time-Bound). They must be directly aligned with the goals.
List the objectives below:
1
2
3
4
5
Step 3: Generate Alternatives
Project Manager Guidelines
Before the meeting:
Determine which areas of expertise need to participate to generate a thorough list of alternatives
Contact the experts in the potential solutions to help you to request their involvement in this step
Make sure the Project Sponsor is aware that solution planning is in progress and has an opportunity to offer comments.
Draft the meeting objectives and agenda
Contact the appropriate experts and request their involvement.
During the meeting:
Brainstorm possible solutions to achieve the defined goals and objectives
Address the question: “Does this need/problem exist in other organizations and how are they solving it today?”
Conduct analysis of the various alternatives (see Analysis Considerations below)
Document the Alternatives
After the meeting:
Identify, from Project Sponsor and Requester, who should be involved in the decision-making process
Schedule the meeting for Step 4: Determine Solution and Approach(es) (include Project Sponsor, Project Requester, Solution Experts, and anyone else as identified by the Project Sponsor and Requester)
Team Guidelines
When assembling the Solution Planning team, be sure to consider :
Which areas of expertise need to participate in solution planning (you may first need to consult with various solution planning resources)
Appropriate solution planning representation, including those who would be aware of what solutions may already exist in other areas of the organization
If the project may potentially affect the infrastructure, include experts from the corresponding organization(s)
If the project may have a process component (i.e. a process needs to be improved or a root cause needs to be investigated), involve a process expert
The role of the solution planner is to:
Think in the best interests of the enterprise
Understand all impacts
Consider all alternatives
Fairly evaluate all alternatives
Point out both positive and challenging aspects of the alternatives
Note: Successful solution planning requires broad input to ensure that all reasonable alternatives are considered.
Effective solution planning requires that the right experts be available for project-specific solution planning activities. If the desired solution planner cannot participate in solution planning in the needed time frame, they should suggest a delegate.
Solution planning is not intended to address resource requirements. The project resource needs will depend on the solution selection. Project resource assignments happen after the project has been authorized, funded and prioritized against other projects in the portfolio.
Analysis Considerations
When analyzing alternatives and their risks and benefits, the checklist below may help. Not all of these questions need to be answered, but all should be considered to determine their relevance.
Delivering Business Processes:
· What process functionality is being delivered (i.e., what does the process need to do)?
· Is it new or will it change existing processes and enabling systems?
· Will elements of the business need to reorganize around the delivered solution? If so, which elements?
· What is the extent of the changes that will take place (e.g., new to some, not new to others)
· What are the connection/interfaces and impact to other business processes?
· What equipment (e.g., hardware, software) or custom development may be required to implement the solution?
· How much testing/inspection has to be done (what level of quality is acceptable) and who needs to participate?
· What training needs to be developed and delivered?
· What documentation is required?
· Will other business/functions within the company be able to use this solution?
Capacity:
· Are there any capacity issues that need to be addressed; people, bandwidth, storage, computing power, response time, transactions?
Technology:
· What technology is being considered for this project? Is it new in the industry? Is it new to the company?
· Where is this technology in its maturity life cycle? If the solution is not part of the enterprise today, is there a compelling reason why?
· Is this a known “throw away” deliverable (short life cycle)?
· Are there licensing requirements or other restrictions to use?
Security:
· Are there any access issues that will need to be addressed?
· Are there any proprietary information issues that need to be addressed?
· Will access need to be provided for external resources; customers, suppliers, warehouses, Joint Venture partners, others?
· Are there any business controls or segregation of duties issues that will need to be addressed?
· What business interruption/continuity issues need to be addressed?
Risk Management:
· What is the technical risk of the solution?
· Will the solution provide all the required functionality? What is the impact if it doesn’t?
· Will the users use it? What happens if they don’t? What do we need to do to maximize utilization?
· What is the potential risk to the organization if there is a security breach?
· What other risks exist?
Cost:
· What is the total cost of ownership of the solution (including ongoing support and maintenance)?
Alternatives
In the following grid, list the possible alternatives (along with benefits, risks, and a conceptual estimate). Include non-capital alternatives and the “do nothing” alternative.
# | Solution | Benefits |  | Risks |  | Conceptual Estimate | Recommendation & Reasoning (Strong, Possible, Weak & Why)
1
2
3
4
5
6
7
8
9
10
Step 4: Determine Solution(s) and Approach
Project Manager Guidelines
Before the meeting:
Prepare for the meeting:
- Draft meeting objectives and agenda
- Review alternatives for completeness and send as pre-read
During the meeting:
If necessary, revise objectives (i.e. the chosen solution(s) may necessitate adding or changing objectives in this document – prepare recommendations for Sponsor approval.)
Confirm strategic fit (make sure the chosen solution fits with the need and strategies outlined in the problem determination section)
List the chosen solution(s) and the roles required
Confirm that the sponsor will and is prepared to proceed to Governance
After the meeting:
Distribute meeting output and Sponsor decision regarding proceeding to Governance
Begin working on the Business Case, with input from the Project Sponsor
Chosen Solution
Summarize the chosen solution(s), and why they were selected:
List the items that are in and out of scope for the chosen solution(s) – as much as is known at this point and as adequate to offer an order of magnitute estimate. This will be elaborated during project planning, once approved.
Describe the approach that will be used for managing the project (e.g., Start > Do > Deliver, Six Sigma, IPECC, Phased, etc.):
List the roles established for the project, and those that will be required to proceed with the chosen solution(s)
Requester(s):
Sponsor:
Steering Team:
Project Manager:
Key Contacts/Subject Matter Experts:
Others (add as needed):
Document Revision History
Date | Changed by | Requested by |  |  | Description of Change |  | Section
Document Review/Approval History
Date | Reviewed by | Approved by |  |  | Comments
Sponsor
Steering Team Member A
Steering Team Member B

## BizCase
Business Case
The approved business case can be found at: |  | <insert link here if the approved business case is stored elsewhere>
Summary information:
Sponsor: | <Name> |  |  |  |  | We highly recommend moving forward with this project!
Date submitted: | [5 empty] | SUMMARY
Decision: | <Approved, Rejected, Recycled, On hold, etc…> |  |  |  |  | Cost: | 88000
Decision date: | [5 empty] | Benefits: | 190000 | 4 Years + Ongoing
Decided by: | <Name or Approval Body including member names> |  |  |  |  | Breakeven: | 2.1591 | Years
Budget approval breakdown: |  | Capital | Expense | Total
| Internal | 10000 | 50000 | 60000
| External | 10000 | 10000 | 20000
| SubTotal | 20000 | 60000 | 80000
| Contingency | 2000 | 6000 | 8000 | 10%
| Total Estimate | 22000 | 66000 | 88000
Ongoing costs expected: | 10000 | Per year
Ongoing costs approved by:
Benefits expected: | Y1 | Y2 | Y3 | 3 Year-Total | Ongoing
| 40000 | 50000 | 55000 | 145000 | 55000
Terms for Benefits Realization: | Sponsor will…
<Explain what the Sponsor will do to capture benefits.>
Schedule expectations: | Start | Do | Deliver
Expected completion dates: | 2003-01-02 | 2004-02-03 | 2004-03-04
Resources approved: | Resource Hours | Equivalent Cost
Low Estimate | 400 | 40000
High Estimate | 500 | 50000
Assumptions: | The business case costs and benefits are based on the following assumptions:
1
2
3
About this Document:
Once the project is initially defined, develop the business case to estimate cost vs. benefit. We first prove to ourselves that this project is worth our investment (time/money).
If your organization has it's own requirement for requesting funding and/or resource approval to move forward with a project, use it instead and capture the highlights here.
Having the highlights here makes it easier for you to reference, explain to the team, and remind everyone why the project is worth it when the project gets difficult.
The Business Case "thinking tool" helps to answer 3 key questions: 1) why this project? 2) why now? 3) is it worth it?
The above elements about cost vs. benefit are focused on "is it worth it?" There is generally a business reason for "why THIS project" and "why now."
The Sponsor then often needs to "make the case" to request organizational commitment for resources to work on the project (e.g., monetary, people, space, equipment).
If you do not have capital and expense financial rules to worry about, eliminate those differences above. If you do, get the rules from the finance department.
It is good practice to include estimated internal resource hours (and don't forget about the project manager's time!) in the case, because time is money.
For instance, if a project is going to save 1 person 1 hour of time once per year but cost 100 hours for someone to complete, does that seem worth it? A "no go" here is a win!
We tend to choose an hourly rate to make comparing projects and the benefits easy. For example $100/hour for everyone. Later, you can ask accounting for the actual rate.
Generally organizations have forms for requesting capital spend. For your easy reference throughout the project, input the information from that document below.
If the project is expense, you may choose to adopt similar requirements.
Document Revision History
Date | Changed by |  |  | Requested by |  |  | Description of Change |  | Section
Document Review/Approval History
Date | Reviewed by |  |  | Approved by |  |  | Comments
Sponsor
Steering Team Member A
Steering Team Member B
Capital/expense rules
As of: | <date>

## Agree
Project Agreement
Project Executive Summary
Briefly summarize the most important aspects of the project by briefly answering the questions “Why?” (problem/opportunity, strategic alignment,
and benefits), "What?" (goals/product description/ scope), "When?" (time), “Who?” (key stakeholders), and "How much?" (resources/cost).
Objectives
The quantifiable criteria that must be met for the project to be considered successful. The best objectives are SMART (Specific, Measurable, Achievable, Realistic, Time-bound). Explain the project will be managed keeping the 5 force ranked Delivery Objectives in mind (e.g., 1. Time because..., 2. Stakeholder Sat because..., etc.)
Deliverables
A list of the summary-level products and subproducts whose full and satisfactory delivery marks completion of the project. Deliverables are "tangible" and "verifiable."
Project Scope
In Scope
Clearly define what is in scope for the project, including process changes and people aspects (e.g., change, communications, training). | Clearly define what is in scope for the project. Please include any process changes that are in scope.
Out of Scope
Clearly define what is not in scope for the project. Note that all items clearly not listed as in scope are out of scope. | Clearly define what is not in scope for the project. Note that all items clearly not listed as in scope are out of scope.
High Level Milestone & Gate Schedule
Identify the significant events that mark the progress of the project, gate reviews, and the expected delivery schedule. At a minimum, include phases/key deliverables. Ideas are below. Modify as required for your project.
Milestone/Gate |  |  |  | Schedule
1. Project Sponsor signs-off on initial Project Agreement (this document)
2. Baseline approved (Mandatory Stage Gate: Baseline Approval)
3. Project Kick-off
4. Product Design Approved (Stage Gate: Design Review)
5. Implementation Go/No Go Decision Made
(Stage Gate: Pre-implementation Review)
6. Product Delivered/Implemented (Mandatory Stage Gate: Final Review)
7. Project Closing Complete
8.
9.
10.
11.
Top Risks & Responses
Describe the major risks (most likely, highest impact) to achieving the project objectives on time, on budget, on scope, on quality with a high degree of stakeholder satisfaction. "Response Plans" are the recommended actions you will take to avoid, mitigate, transfer or accept these top risks.
Top Risks (Most Likely, Highest Impact) |  |  | Response Plans
1. |  |  | 1.
2. |  |  | 2.
3. |  |  | 3.
4. |  |  | 4.
5. |  |  | 5.
Assumptions
Describe major assumptions related to the project. Assumptions are factors that, for planning purposes, are considered to be true, real, or certain.
Constraints
Describe major constraints associated with the project in terms of time, cost, and scope/quality. Constraints limit the options of the project team. They may affect the performance of the project (e.g., any factor that affects when an activity can be scheduled).
Project Organization
List project roles and key contacts. Modify as required for your project.
Role |  |  | Name(s)
Project Sponsor
Steering Team Members
Project Manager
Project Team
Stakeholders
About this Document:
This document is used to gain agreement to move forward with the project as described.
Upon agreement, this document will serve as a basis for future project decisions.
Changes after agreement are subject to a formal change management process.
Document Revision History
Date | Changed by | Requested by |  | Description of Change | Section
Document Review/Approval History
Date | Reviewed by | Approved by |  | Comments
Sponsor
Steering Team Member A
Steering Team Member B
(select one)
Regional
Global
(select one)
Single Business
Multiple Businesses
Enterprise
Note on A1: Similar to the PMI Scope Statement Definition (PMBOK, 4th Ed.) The narrative description of the project scope, including major deliverables, project assumptions, project constraints, and a description of work, that provides a documented basis for making future project decisions and for conﬁ rming or developing a common understanding of project scope among the stakeholders.
Note on A67: The individual responsible for managing the project.
Note on A68: The group that is performing the work of the project under the leadership of the project manager.
Note on A69: Individuals and organizations that are actively involved in the project, or whose interests may be positively or negatively affected as a result of project execution or project completion; they may also exert influence over the project and its results.

## MgmtPlan
Management Plan
Management Topic |  |  | Suggested Approach/Example
Project Management Approach: (describes the project management approach used) |  |  | This project will follow the Start -> Do -> Deliver best practice approach to deliver the business, management, and technical requirements of this project.
Scope / Deliverables Management: (specific approval/acceptance process and the turnover of project deliverables) |  |  | Scope/Deliverables Management is accomplished by: • Defining basic scope parameters in the Project Agreement such as geography and what is out of scope • Creating, receiving Project Sponsor acceptance of, baselining, and managing changes to the Work Breakdown Structure (Deliverables Breakdown) and its corresponding Deliverables Dictionary, which shows and clearly defines ALL of the deliverables that will be produced during the project • Ensuring that deliverables meet the objectives of the project • Managing expectations of the project stakeholders • Submitting/reviewing each deliverable with the Project Sponsor or other appropriate leader • Reviewing and accepting/rejecting deliverables in a timely manner • Submitting/reviewing deliverables as part of the formal stage gate reviews, as appropriate
Quality Management: (Use this section to identify any Quality Assurance / Quality Control activities that are being implemented for the project and product to ensure project success. Examples include usage of: 1) standard methodology 2) stakeholder satisfaction survey 3) draft deliverable walkthroughs 4) peer reviews 5) use of checklists 6) lessons learned 7) acceptance / sign-off |  |  | Quality Planning and Management is accomplished by: • Using the appropriate quality processes and tools/techniques • Reporting suggestions for process improvement to improve quality of future projects • Participating in random audits by XYZ department • Building quality into the project schedule and ensuring the right skilled resources are available and assigned to perform quality tasks (e.g., peer reviews, quality assurance reviews by one or more senior-level team members, reviews to ensure deliverables match specifications) • Following the appropriate industry and/or corporate standards for quality
Cost / Resource Management: (how human and other resources will be assigned, managed and released) |  |  | A budget will be approved and baselined. Use the Resource Plan & Budget to estimate the resources (labor, non-labor) needed over the course of the project and organize your project budget. Actual costs will be tracked against the budget. Vendor invoices will be carefully reviewed and approved or rejected. Approved invoices will be paid per finance policy (e.g., NET 30) Spending will be forecasted in the budget by month and actual spending will be tracked and reported by month. In creating the budget, cost categories to consider include but may not be limited to: • Internal and external human resources • Cost to acquire external equipment, space, supplies, etc • Travel and related expenses • Contingency for changes and risks at an agreed upon % approprate to the project's complexity and confidence that costs have been thoroughly understood • Other costs required (e.g., some organizations also require a % allocation for communication expenses, space, etc.) Resource management is accomplished by: • Working with department leaders/experts to identify the skills, equipment, etc. necessary to accomplish the objectives and produce the deliverables required • Estimating the amount of time required by skill and securing commitment for that time as per the project schedule • Resource managers transferring responsibility for project task management to the Project Manager • Project managers and resource managers agreeing on when the resource will be released from the project, with the project manager keeping the resource manager informed of any changes • Project managers providing resource managers with performance input after the resource has been released from the project with the expectation being that the input will be used fairly during the annual performance review
Schedule / Task Management: (how to plan and keep the project on time; how the work will be assigned, status obtained, and progress analyzed) |  |  | Schedule & Task management is accomplished by: • Working with the team to define the tasks and record them in the schedule (MS Project will be used) • The agreed-upon schedule will be baselind and the actual progress will be reported against the plan/baseline • "5-7" Milestones will be determined and we will focus our efforts on achieving next milestone dates; only the Sponsor/Steering Team can approve a change to the milestone dates after thorough analysis of options to stay on time • Reporting percent-complete on a regular basis (e.g., ~every 2 weeks) per the agreed-upon count it or Keep it Simple method (0%, 25% started, 99% submitted and waiting on approval, 100% complete) • Tracking time spent in the Time/Cost tracking system X
Issues/Actions Management: (how issues, problems, action items are managed) |  |  | Issues/Actions Management is accomplished by: • Following a documented problem/issue management process to document, track, resolve, and escalate exceptions as appropriate • Using the Rolling Actions and Issues Log (RAIL) for issue/action tracking • Escalating issues beyond the power of the Project Manager to the Project Sponsor and/or Steering Team, PMO Director and/or Business Unit Director for resolution as appropriate
Change Management: (how project changes are addressed) Changes that modify the agreed-upon scope, date, or cost targets must be actively managed, particularly when any of the following occur: • A request or need to add/reduce/change deliverables • Deviation from the promised cost estimate range • Deviation from any promised milestone or project-end target dates • Changes to assumptions that impact one of the above • An unforeseen event that impacts one of the above |  |  | Change Management is accomplished by: • Communicating the approved baselines (scope, time, budget) and the change management process to team members and project leadership; managing change moving forward • Recording all change requests (whether approved or not) in the Change Log • Assigning the change requestor to define the details • Defining with project leadership the change approval levels (time/cost). Project manager may approve up to $X per change and inform project sponsor. Project Sponsor may approve up to $XX per change and inform Steering Team. Steering Team approves all other changes. • Receiving approval from the appropriate project leadership level and only implementing approved changes • Updating all related documentation after the change has been approved
Risk Management: (how risks are identified and managed) |  |  | Risk Management is accomplished by: • Understanding the risk tolerance of key project stakeholders and managing risk accordingly • Considering potential risks and their impact on the project • Taking action to avoid, mitigate, transfer or accept risks as appropriate • Esalating as needed and responding to risks as appropriate • Defining and tracking risks on a regular basis using the Risk Analysis and Response Worksheet
Stakeholder & Communications Management: (how communications will be planned and managed) |  |  | Stakeholder & Communications Management is accomplished by: • Identifying, analyzing stakeholder needs and planning how to manage those needs throughout the project using the Stakeholder Analysis & Management Matrix (SAMM). Since a key way to manage stakeholders is through communicating effectively and at the right frequency... • Planning and documenting communications in the Communications Plan (located within the SAMM worksheet)at the beginning of the project (this includes identifying what, when, and how items will be communicated to whom) • Executing the agreed-upon Communication Plan
Procurement Management: (how purchases will be managed) |  |  | Procurement Management is accomplished by: • Planning purchases of people, software and equipment, conducting “make or buy” analysis, meeting with vendor(s), and requesting information as needed Note: If the Project Manager meets with the salesperson or requests information, the Project Manager is not to commit to anything or indicate that the vendor has been selected. This typically reduces the effectiveness of the contract negotiation. • Notifying the organization's Procurement Representative at the very beginning of this process, to determine if certain vendors are recommended • Providing content and other information as needed to Procurement as they prepare procurement documents, if appropriate, (e.g., Requests for Information (RFI), Requests for Proposal (RFP)) • Negotiating a contract (this is the responsibility of Procurement) • Cutting a purchase order (this is the responsibility of Procurement) • Managing the vendor and related internal resources effectively • Escalating issues regarding vendor performance to Procurement as needed
Status / Progress Reporting: (what types of status and progress reporting will be generated, report format, distribution and frequency) |  |  | Status/Progress Reporting includes: • Tracking and reporting progress against time, cost, and scope baselines as well as quality and stakeholder satisfaction expectations using input reported by team members • Providing Earned Value reporting for time and cost status, and major milestone and issue reporting • Using the Project Status Report to report the TRUE status of the project on a regular basis • Defining formal stage gates during which progress to date is reported and approval to proceed is granted • Determining what actions to take to get projects back on track and gaining Project Sponsor or other stakeholder agreement/commitment to take action, as appropriate
About this Document:
· Once complete, serves as a guideline for how the project will be managed, assisting the Project Manager and Sponsor in setting expectations early.
· The Suggested Approach/Example column provides an example from which to create your plan for managing this project.
· The Project Manager should modify as appropriate, gain agreement from the Sponsor and review with the team.
Document Revision History
Date | Changed by | Requested by |  | Description of Change | Section
Document Review/Approval History
Date | Reviewed by | Approved by |  | Comments

## Deliverables
Deliverables Breakdown
Deliverables Dictionary
| Deliverable |  | Approved | Accountable | Submitted for | Accountable for |  | Acceptance/ | Baseline
ID | Name | Description | By | for Delivery | Inspection/Acceptance | Acceptance | Accepted On | Inspection Notes | or Change ID
|  |  | Name | Name | 2010-10-10 | Name | 2010-10-10 | Accepted. | Baseline
|  |  | Name | Name | 2010-10-10 | Name | 2010-10-10 | Acceptable for go live but add X to punch list. | Baseline
|  |  | Name | Name | 2010-10-10 | Name | 2010-10-10 | Acceptable for go live but add X to punch list. | Baseline
|  |  | Name | Name | 2010-10-10 | Name | 2010-10-10 | Acceptable for go live but add X to punch list. | Baseline
|  |  | Name | Name | 2010-10-10 | Name | 2010-10-10 | Acceptable for go live but add X to punch list. | Baseline
About this Document:
The Deliverables Breakdown and corresponding Deliverables Dictionary organize and deﬁnes the total scope of the project.
The Project Management Institute (PMI) calls this the Work Breakdown Structure (WBS)
Here we "break down" the work into small enough pieces that it can be assigned to project team members.
Deliverables are directly aligned to project objectives so that ONLY the deliverables required are included.
Deliverables are tangible and verifiable things. They are not tasks.
If the deliverable is not included, it is NOT in scope.
Upon approval, this becomes the scope baseline and any changes are managed through the change management process.
Scope Management Tips
1 | The Project Management Plan provides the specific approach to deliverables management and sign-off for a given project.
2 | Ensure delivery dates are included in your schedule for each deliverable. They are not to be included here.
3 | Color-code the deliverables by organization responsible for completing them for an easy visual.
4 | Formally document acceptance of project deliverables as they are completed.
5 | Include a checkmark on the boxes when the deliverables are completed for an easy visual on delivery status.
6 | Obtain final sign-off indicating acceptance of the complete project and all of the final deliverables.
7 | Generally scope changes lead to other changes like cost/resources and schedule changes. Be sure to follow the change management process.
8 | Define the deliverables clearly using the Deliverables Dictionary.
Document Revision History
Date | Changed by |  |  | Requested by |  |  | Description of Change |  |  | Section
Document Review/Approval History
Date | Reviewed by |  |  | Approved by |  |  | Comments
Name of Project
Project Management
Deliverable, Phase or Category 2
Deliverable, Phase or Category 3
SubDeliverable 1.1
SubDeliverable 2.1
SubDeliverable 3.1
SubDeliverable 3.2
SubDeliverable 2.2
SubDeliverable 1.2
SubDeliverable 1.3
SubDeliverable 2.3
SubDeliverable 3.3
Deliverable, Phase or Category 4
SubDeliverable 4.1
SubDeliverable 4.2
SubDeliverable 4.3
Deliverable, Phase or Category 5
SubDeliverable 5.1
SubDeliverable 5.2
SubDeliverable 5.3


## StatusLong
<Project Name> Status Report
|  |  | As of: | <Date>
Number: |  |  |  | Current Overall Assessment: |  |  | Green | On-plan
PM: |  |  |  | Organization Level 1:
Sponsor: |  |  |  | Organization Level 2:
Steering Team: |  |  |  | Organization Level 3:
Start Date: | 2010-01-01 |  |  | Projected End (Baselined): |  |  | 2011-02-10 | (27-Dec-2010)
Executive Summary
Provide a brief overview of the status of the project at this point in time, along with any major issues that need to be addressed.
Objective: | To achieve….
The program is slightly behind schedule due to the inability of resources to be assigned on time to begin the work.
Milestones / Deliverables Status
Brief explanation of current and next milestone/deliverable
(List all key project milestones/deliverables and report current status information):
Item |  | Milestone or Deliverable |  | Original Date | Forecast Date | Actual Date | Comments
Project and Financial Summary:
Original Budget: $ |  | Approved Changes: $ |  |  |  | Current Budget: $
Original Target End Date: |  | Approved Revised End Date: |  |  |  | Current Target End Date:
Percent Complete: |  | Schedule Performance Index (SPI): |  |  |  | Schedule Variance % (SV%):
Actual Cost: $ |  | Cost Performance Index (CPI): |  |  |  | Cost Variance (CV):
Current Estimate at Completion (EAC): $
Variance Explanation (and what actions are being taken to resolve any variance):
Supporting Details
Progress Report: (what is completed, what is in process, key changes made, when and why, etc.)
** Also attach progress curve charts
Forecasting: (estimate of future project status and progress)
** Also attach progress curve charts
Status of Project Relative to Project Objectives (place in priority order):
Scope |  |  |  |  | Scope brief comment if Yellow or Red |  |  |  | Green
<Explain any variance - why off-scope, impact to objectives, response)>
Schedule
<Explain any variance - Ahead or behind schedule by how much, why, response>
Cost
<Explain any variance - Under or over by how much, why, response>
Quality (On/off quality, impact, response)
<Explain any variance - Ahead or behind schedule by how much, why, response>
Resources (on/off plan, impact, response)
<Explain any variance - Ahead or behind schedule by how much, why, response>
Stakeholder Satisfaction (different stakeholder groups satisfied?, comment as to evidence, impact, response)
<Explain any variance - Ahead or behind schedule by how much, why, response>
Issue: |  |  |  |  | Who Will Address:
Insert a brief description of the top few issues
Risk and Impact: |  |  |  |  | Risk Response:
Insert a brief description of the top risks and their impact |  |  |  |  | Brief description of the response planned
Status Report Submitted to:
Name: |  |  | Title: |  |  |  | Date:
Name: |  |  | Title: |  |  |  | Date:
Name: |  |  | Title: |  |  |  | Date:
Attachments:
Progress Curve Charts
About this Document:
Use this document to think through project status prior to submitting to the portfolio manager.
Use this exercise as an opportunity to think through what should be done to ensure the project stays on track.
Ensure you know key and have quick access to project status information at all times.

## Status1pg
|  | Sponsor Update |  |  |  |  | Prepared by: |  | Also availabe in PowerPoint
<Name>
<Email>
<Phone>
<Project Name> |  |  |  | Status: |  | 100% | <Brief Status Comment>
Objective
Sponsor
Summary | The Sponsor update summary is....
Schedule | Scope |  | Cost & Effort |  | Quality |  |  | Satisfaction | KEY
100% | 90% |  | 70% |  | 70% |  |  | 20% | Color | Brief Description
Status is…. | Status is…. |  | Status is…. |  | Status is…. |  |  | Status is…. | 20 | RED - Off plan or no approved plan in place. Focus is needed to get back on track.
[9 empty] | 50 | YELLOW - In danger. Focus is needed to avoid RED status and return to GREEN.
[9 empty] | 100% | GREEN - On plan. Focus is needed to stay on track.
[9 empty] |  | GRAY - Not applicable.
[9 empty] |  | BLUE - Complete
Resources | Issues&Actions |  | Risks |  | Milestones |  |  | Comments
Status is….
Copy/Paste Above….
0 | 0 |  | 0 |  | 0 |  |  | 0
50 | 50 |  | 50 |  | 50 |  |  | 50
100% | 100% |  | 100% |  | 100% |  |  | 100%

## Change
Change Log
ID | Brief Description | Benefit / Value | Impact Description | Requested By | Requested | Decision | Decision By | Decision | Decision Status Comment | Requestor | Impact | Work Effort | Cost | Resources | Approach / Alternatives Considered
[5 empty] | Date |  |  | Date |  | Notified | (Days) | (Hours) | Estimate
1 | Description… | Benefit of the change… | Impact of the change… | Name | 2000-01-01 | Pending | Name | 2000-01-01 | Awaiting information from requestor | 2000-01-01 | 1 | 8 | 800 | A. Mahan
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
About this Document:
This document provides easy record keeping for change requests and the corresponding impact analysis and approval/rejection
decision process, assisting the project manager in continually managing expectations and keeping the project "on plan."
Once baselined, all changes must be reviewed by the project manager so that impact on the project can be assessed
and an informed decision can be made by all appropriate parties.
The formal change management process is described in more detail in the Management Plan.
Note on C3: Briefly describe the reason for the requested change and the benefit.
Note on D3: Provide a brief description of the impact of this change on this project and other projects including time, cost and resources.
Note on O3: Resources or skills required to implement the change
Note on P3: Explain the alternatives considered and the selected approach to implement the requested change.
Note on J4: 1. Awaiting Information from Requestor 2. Analyzing Impact 3. Rejected 4. On Hold 5. Approved

## Schedule
Program Level Schedule
| Description | Lead | Pre-work | 2015-05-11 | 2015-05-18 | 2015-05-25 | 2015-06-01 | 2015-06-08 | 2015-06-15 | 2015-06-22 | 2015-06-29 | 2015-07-06 | 2015-07-13 | 2015-07-20 | 2015-07-27 | 2015-08-03
Kickoff
1 | Initial project definition & Plan | Dawn
2 | Sign-off/Agreement | Rick
Workstream - Business Advisor Secured
Goal: To choose business advisor.
1 | Define Selection Criteria & Identify Candidates | Rick
2 | Create RFP and Send | Dawn
3 | Review Proposals & Analyze Against Criteria | Dawn |  |  |  |  | Firms Respond
4 | Panel Review of Candidates & Selection of Top 2 | Rick
5 | Negotiation with Top 2 | Rick
6 | Contract with Selected Candidate | Michael
Workstream - Legal Advisor Secured
Goal: To choose legal advisor that will work well with the selected business advisor.
1 | Define Selection Criteria & Identify Candidates | Michael
2 | Business Advisor provides input on candidates | Dawn
3 | Selection of Top 2 Candidates | Michael
4 | Negotiation | Michael
5 | Contract | Michael
Transition
Goal: To successfully transition to selected advisors, kickoff the next phase and close this one.
1 | Onboard and Transition Knowledge | Dawn
2 | Kickoff | New advisor
3 | Close | Dawn
Training Partnerships
1 | Training Descriptions & Pricing
2 | Webinar
3 | Partner X Review Latest
4 | Partner Y Agreement & Launch
5 | Partner Z Agreement & Launch
| Color Key | Started | Not Started
Notes
1
2
3
4
5

## Resource&Budget
Resource Plan & Budget
Resource Plan | [10 empty] | Resource Plan
ID | Resource | Role | Org | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1 | Fiona | Project Manager | ABC Home Improvement | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Name | <<WHO DO YOU NEED>> | [6 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
3 | Name | [7 empty] | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
4 | Name | [7 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
5 | Name | [7 empty] | 1 | 1 | 1 | 1 | 0.5 | 0.25
6 | Name | [7 empty] | 1 | 1 | 1 | 0.5 | 0.25
7 | Name
8
9
10
11
12
13
14
|  |  |  | 0 | 0 | 0 | 0 | 0 | 3.8 | 3.8 | 3.8 | 3.3 | 2.55 | 2.05 | 1.8
Budget - Detailed Labor & Non-Labor Estimates | [10 empty] | Budget - Detailed Labor & Non-Labor Estimates
| LABOR COST ESTIMATES |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Day Rate
ID | Resource | Role | Org | 20 | 20 | 23 | 22 | 20 | 22 | 21 | 22 | 21 | 21 | 20 | 22 |  | <--Business Days per Month (for a more accurate estimate)
1 | Fiona | Project Manager | ABC Home Improvement | 0 | 0 | 0 | 0 | 0 | 17600 | 16800 | 17600 | 16800 | 16800 | 16000 | 17600 | 800
2 | Name | <<WHO DO YOU NEED>> | 0 | 0 | 0 | 0 | 0 | 0 | 3520 | 3360 | 3520 | 3360 | 3360 | 3200 | 3520 | 800
3 | Name | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1760 | 1680 | 1760 | 1680 | 1680 | 1600 | 1760 | 800
4 | Name | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8800 | 8400 | 8800 | 8400 | 8400 | 8000 | 8800 | 800
5 | Name | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17600 | 16800 | 17600 | 16800 | 8400 | 4000 | 0 | 800
6 | Name | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17600 | 16800 | 17600 | 8400 | 4200 | 0 | 0 | 800
7 | Name | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800
| NON-LABOR COSTS |  | Responsible | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Totals
15 | Equipment |  | PM |  |  | 10000 | [9 empty] | 10000
16 | Telephony |  | PM |  | 100 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 2600
17 | Travel expenses |  | PM |  | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 250 | 10250
18 | Teambuilding and Kickoff |  | PM |  |  | 750 | [9 empty] | 750
19 | Supplies - Training binders, etc. |  | PM | [8 empty] | 1000 |  |  |  | 1000
20 | Team recognition |  | Sponsor | [5 empty] | 500 |  |  | 500 |  |  | 500 | 1500
Budget - Summary Estimates | [10 empty] | Budget - Summary Estimates
ID | SUBTOTAL ESTIMATED LABOR COSTS |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Totals
21 | Estimated labor spend by month |  |  | 0 | 0 | 0 | 0 | 0 | 66880 | 63840 | 66880 | 55440 | 42840 | 32800 | 31680 | 360360
22 | Estimated labor spend by quarter |  |  |  |  | 0 |  |  | 66880 |  |  | 186160 |  |  | 107320 | 360360
23 | Estimated labor annual total |  |  | 360360
SUBTOTAL ESTIMATED NON-LABOR COSTS
24 | Estimated non-labor spend by month |  |  | 0 | 1100 | 12000 | 1250 | 1250 | 1750 | 1250 | 1250 | 2750 | 1250 | 1250 | 1000 | 26100
25 | Estimated non-labor spend by quarter |  |  |  |  | 13100 |  |  | 4250 |  |  | 5250 |  |  | 3500 | 26100
26 | Estimated non-labor annual total |  |  | 26100
SUBTOTAL ESTIMATED COSTS WITH NO CONTINGENCY
27 | SubTotal - Labor + Non-Labor by month |  |  | 0 | 1100 | 12000 | 1250 | 1250 | 68630 | 65090 | 68130 | 58190 | 44090 | 34050 | 32680 | 386460
28 | SubTotal - Labor + Non-Labor by quarter |  |  |  |  | 13100 |  |  | 71130 |  |  | 191410 |  |  | 110820 | 386460
29 | SubTotal - Labor + Non-Labor annual total |  |  | 386460
CONTINGENCY ESTIMATES
30 | Contingency by month |  | 10% | 0 | 110 | 1200 | 125 | 125 | 6863 | 6509 | 6813 | 5819 | 4409 | 3405 | 3268 | 38646
31 | Contingency by quarter |  |  |  |  | 1310 |  |  | 7113 |  |  | 19141 |  |  | 11082 | 38646
32 | Contingency annual total |  |  | 38646
GRAND TOTAL ESTIMATED COSTS WITH CONTINGENCY
33 | Total Costs by Month |  |  | 0 | 1210 | 13200 | 1375 | 1375 | 75493 | 71599 | 74943 | 64009 | 48499 | 37455 | 35948 | 425106
34 | Total Costs by Quarter |  |  |  |  | 14410 |  |  | 78243 |  |  | 210551 |  |  | 121902 | 425106
35 | Total Cost Estimate |  |  | 425106
<PROJECT NAME>
Management Summary - Cost Estimates as of <DATE>
|  |  | Estimates | Q1 | Q2 | Q3 | Q4 | Totals
|  |  | Labor | 0 | 66880 | 186160 | 107320 | 360360
|  |  | Non-Labor | 13100 | 4250 | 5250 | 3500 | 26100
|  |  | Contingency | 1310 | 7113 | 19141 | 11082 | 38646
|  |  | Total | 14410 | 78243 | 210551 | 121902 | 425106
Assumptions
|  |  | Contingency | 10% | The team has high confidence in the estimates.
#Resources
Non Labor costs include….
Etc…
Contract Tracking - Procured Labor & Non-labor Summary
ID | Vendor | Description | Contract Signed (Date) | Start (Date) | End (Date) | Amount | Key Terms | Contract Doc Location
1 | <Name>
2
3
4
5
6
7
About this Document:
Use the Resource Plan & Budget to estimate the resources (labor, non-labor) needed over the course of the project and organize your project budget.
The Resource Plan section can be used to communicate expectations and manage resource on-boarding and exits. This is NOT the project schedule.
Additionally, it is best practice to include a contingency factor that is in alignment with risk and confidence levels.
Should you procure needed labor and non-labor through contracts, you may use the Contract Tracker to help manage these resources and costs.
By estimating project costs by labor, non-labor and a fair contingency estimate and breaking them all out by month, quarter and annually up front,
you will be able to quickly answer nearly any management cost estimate question and create summaries in the way they need to see them.
Change the plan document for your purposes and enjoy the benefits of being prepared!
Note: For simplicity, capital and expense costs are not differentiated here. If you have a mixed project, you need to modify the XLS accordingly.
Document Revision History
Date | Changed by |  | Requested by | Description of Change |  |  |  |  | Section
Document Review/Approval History
Date | Reviewed by |  | Approved by | Comments
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 = 100% of a resource during this month. .5 = 50% … fill in the right time allocation that makes sense for your resources you need across the months.
Note on D61: TYPE IN THE CONTINGENCY % THAT MAKES SENSE FOR YOUR PROJECT

## Org&RACI
Project Organization Chart
RACI Chart
ID | Major Activities | Sponsor | Steering Team | Project Manager | Project Team | Workstream Lead | Customer Rep | [Enter add'l Role]
1 | Project Leadership | A | R | R | I | C | C
2 | Project Plans | C | I | A | C | R | C
3 | Product Deliverable Creation | I | I | C | R | A | C
4 | Product Deliverable Sign-off | C | I | R | I | R | A
5
6
7
8
9
10
11
12
13
14
15
Legend:
R = Responsible (the Do-ers)
A = Accountable (the Owner – only 1 per row)
C = Consult (before doing)
I = Inform (after doing)
About this Document:
This document is used to gain agreement on and communicate project leadership and team roles and responsibilities.
Upon agreement, this document will serve as a basis for future project decisions.
Changes after agreement are subject to a formal change management process. Resource changes can impact cost and schedule.
Document Revision History
| Date | Changed by |  |  | Requested by |  |  | Description of Change | Section
Document Review/Approval History
| Date | Reviewed by |  |  | Approved by |  |  | Comments
Project Sponsor
Name
Project Manager
Name
Workstream A
Leader Name
Workstream B
Leader Name
Name - Title
Name - Title
Name - Title
Name - Title
Name - Title
Name - Title
Name - Title
Name - Title
Name - Title
Workstream C
Leader Name
Name - Title
Name - Title
Name - Title
Workstream D
Leader Name
Name - Title
Name - Title
Name - Title
Steering Team
Name - Title, Name-Title, Name-Title

## Quality
Quality Tracker
ID | Requirement | Approach | Plan Description | Impact Description | Quality Plan | Quality Plan | Inspection | Inspection | Last Inspection | Approval | Notes
|  | Summary |  |  | Approved | Approved By | By | Date | Result | Date
EX | Product must meet major aesthetic, functional and usability requirements | Design & Inspect | Documented understanding of product requirements/Peer design review / Design sign-off by Customer / Early prototype Customer inspection / Customer sign-off | Consumers will choose competition or will be dissatisfied | 2000-01-01 | B. Berry | B. Berry | 2000-02-02 | 5 Defects found; Re-inspect in 1 week | Pending | Approval expected - defects are minor. Planned in 1 inspection cycle, so still on-schedule.
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
About this Document:
This document provides project managers with a template for discussing quality expectations and how they will be satisfied.
It provides easy record-keeping for agreements and where items are in the process.
Once the plan is created, be sure to update schedule and costs, as needed.
After baselining the quality plan, changes shall be handled by the formal change management process.
The formal change management process is described in more detail in the Management Plan.
Note on C2: Briefly describe the planned approach to ensure the quality requirement is met ((e.g., Design In, Inspect)
Note on E2: Briefly describe the impact if the quality requirement is not met.

## SAMM
| Stakeholder Analysis & Management Matrix (SAMM) | [16 empty] | Communication Plan
Stakeholder Identification |  |  |  | Analysis | [6 empty] | Contact Info
ID# | Stakeholder Group | SubGroup | Contact Point/Stakeholder Name | C/F/S | Engaged | Influence | Impact | Assessment | Stakeholder's Top Concerns | Planned Mgmt Response | Email | Office Phone | Mobile Phone | Other | Assistant Name | Assistant Email | Assistant Phone | Communication Deliverable | Key Messages | Target Audience | Delivery Method | Delivery Frequency | Owner | Draft Due (Date) | Done (Date) | Comments
1 | Family |  | Grandma Smith | C |  |  |  | 0 | Wants to help. | Mrs. Smith will spend an evening with her and her Pinterest board. Listen and share the photos with design elements with the contractor and give her credit. Privately discuss with the contractor that direction isn’t to come from Grandma, even if she sounds convincing, and to direct any confusion to Mrs. Smith to provide clarity. | [7 empty] | Project Kick-off | Communicate project goals and objectives, scope, roles, delivery procedures to be used. | All current and future project team members | Meeting | Once | Sponsor |  |  | PM to create agenda and facilitate
2 | Neighbors | Negative Nextdoor | Mrs. Jones | S |  |  |  | 0 | Noise from the project might disrupt her daytime soap operas. | Bake cookies, make sure she has Mrs. Smith's phone number and invite the Jones Family to the grand opening party. | [7 empty] | Team Status/Action | project task and issue tracking
3 | Neighbors | Reasonable | Bill & Ted LaVerne & Shirley | F |  |  |  | 0 | Don't want to be inconvenienced. | Ask contractor to park vehicles on the Smith lot. Make sure they have Mrs. Smith's phone number and invite them to the grand opening party. | [7 empty] | Status Reporting | project sponsor / steering team lead reporting
4 | [17 empty] | Delivery Review - X | Review X deliverable |  | Pre-read and meeting | Once | <Name of Deliverable Owner>
5 | [7 empty] | 0 | [9 empty] | Invitations
6 | [7 empty] | 0 | [9 empty] | Save the Date
7 | [7 empty] | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0 | [9 empty] | Communications to Consider
13 | [7 empty] | 0 | [9 empty] | Review Stakeholder Analysis to ensure all audiences are considered
14 | [7 empty] | 0 | [9 empty] | Internal Team Meetings
15 | [7 empty] | 0 | [9 empty] | Project Status Reports (formal or email – consider audience needs and preferences)
16 | [7 empty] | 0 | [9 empty] | Status reports from team to Project Manager (via time reporting and informal updates)
17 | [7 empty] | 0 | [9 empty] | General awareness emails, marketing, newsletter, open forums/fairs, etc.
18 | [7 empty] | 0 | [9 empty] | Project SharePoint
19 | [7 empty] | 0 | [9 empty] | Senior Management awareness or status updates as needed
20 | [7 empty] | 0 | [9 empty] | Stakeholder Satisfaction Surveys
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
About this Document:
SAMM assists the project manager in identifying, analyzing and managing project stakeholders. Stakeholder needs must be managed throughout the project to ensure project success.
It is critical that all stakeholder organizations are considered and involved early so as not to overlook critical components, risks, etc.
Once the stakeholders are identified and analyzed, use the communication plan to organize how best to keep them involved and informed. (See Step 2.)
Step 1: Identify Stakeholders
A stakeholder is a "person or organization (e.g., customer, sponsor, performing organization, or the public) that is actively involved in the project, or whose interests may be positively or negatively affected by execution or completion of the project. A stakeholder may also exert inﬂuence over the project, its deliverables and the project team members."
Questions to ask to help you to identify stakeholders
1 | Who has a piece of it – who will have people involved, affected? |  | 6 |  | What processes are expected to be impacted?
2 | Who has a stake in it the outcomes (users, people who has a loss - real or perceived)? |  | 7 |  | What systems are expected to be impacted?
3 | Who is part of leading the project (sponsor, steering team, other leads)? |  | 8 |  | Are there any dependent or related other projects?
4 | What and how are external organizations impacted (customers, vendors, government, etc.) |  | 9 |  | Are there any business continuity, disaster recovery, risk or safety concerns?
5 | What and how are internal businesses/functions affected? |  | 10 |  | What else?
Step 2: Analyze Stakeholders and Determine How Best to Manage Them
90% of a project managers job is communication according to the Project Management Institute (PMI).
Work with SAMM to analyze stakeholders, determine which could most impact your project and determine how to manage them to ensure high stakeholder satisfaction.
Generally managing stakeholders includes focused communications. Use the Contact Info area to organize their contact information for easy access.
Ensure all stakeholders are covered in the Communications Plan.
Document Revision History
| Date | Changed by |  |  |  | Requested by |  |  |  | Description of Change |  |  | Section
Document Review/Approval History
| Date | Reviewed by |  |  |  | Approved by |  |  |  | Comments
Note on G3: 3=High, 2=Medium, 1=Low level of influence in or with your organization
Note on H3: 3=High, 2=Medium, 1=Low level of impact the stakeholder could have on your project
Note on I3: Formula - Influence x Impact; use to ensure you have a plan for managing especially those stakeholders with the highest influence in the organization and could have the most impact on your project first; you can chane to a 5 point scale if you have a lot of stakeholders who need to be differentiated
Note on B33: Definition from A Guide to the Project Management Body of Knowledge (PMBOK Guide) 4th Edition published by the Project Management Institute (PMI)

## Kickoff
Project Kick-off Meeting Agenda
Date:
Time:
Where:
Purpose:
The meeting will communicate the goals, objectives and scope for the project, establish roles and responsibilities of the team members and acquaint everyone with all of the processes and procedures that will be used to manage and deliver the project.
Invitees: | CC:
AGENDA TOPICS
Introductions |  | xx:xx | - | xx:xx
Review Business Case |  | xx:xx | - | xx:xx
Review Project Agreement |  | xx:xx | - | xx:xx
Review and Discuss Management Plan/Protocols |  | xx:xx | - | xx:xx
Review & Complete RACI Chart |  | xx:xx | - | xx:xx
Review Deliverables Breakdown |  | xx:xx | - | xx:xx
Review Communication Plan |  | xx:xx | - | xx:xx
Questions & Answers |  | xx:xx | - | xx:xx
Next Steps (e.g., meeting notes, complete documents) |  | xx:xx | - | xx:xx
About this Document:
The purpose of this document is to provide a sample template for a BASIC kick-off meeting. Larger projects tend to require additional topics.

## Decisions
Decisions & Agreements
ID | Logged | Status | Item & Description (original and updates) | Decision/ Agreement | Expected | Date Closed
| Date |  |  | Made By | Close Date
1 |  | Open |  | Names
2 |  | Closed
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
About this Document:
Record all important decisions and agreements needed and completed here (and not captured elsewhere).

## RAIL
Rolling Action & Issue Log (RAIL)
| Date |  |  |  |  | Close Date | Closed
ID | Logged | Status | Item & Description (original and updates) | Owner | Originator | Expected | Date | Reason/Other Comments
1 | 2001-01-01 | Open |  | Name | Name | 2001-01-01 | 2001-01-01
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
About this Document:
The purpose of the RAIL is to keep the project on track.
By definition, projects are unique, so you should expect the unexpected. During each regular status meeting, use the RAIL to
identify, record and track issues that are impacting the ability of the team to stay on plan. Then, determine and track the actions required to address them.

## Risks
Risk Analysis and Response Worksheet
ID | Risk Description | Impact Description | Impact | Likelihood of | Response Plan | Response Type | Responsible | Potential Triggers | Status
|  |  | Severity | Occurrence
1 | [8 empty] | Active
2 | [8 empty] | Closed
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
About this Document:
Use this document to identify risks and determine the appropriate response. Revisit and record new risks regularly.
Build specific actions into the schedule and reserve budget appropriate for the level of risks you see. Communicate with your sponsor.
Close the ones that have passed and move them to the bottom. Keep impact information as helpful for input to future projects.
Impact Severity: |  |  | Likelihood of Occurrence: |  |  | Response Type:
HIGH - Major impact on overall delivery of project |  |  | HIGH - Unavoidable or very likely to occur |  |  | Avoid - take action to eliminate the possibility of the risk occuring
MEDIUM - Some impact on project milestones |  |  | MEDIUM - Likely to occur and manageable |  |  | Mitigate - reduce the probability or impact
LOW - Workarounds available; minimal impact expected |  |  | LOW - Limited potential to occur |  |  | Transfer - reduce risk by transferring some risk to another party via insurance, contract, etc.
Accept/Active - accept with contingency
Accept/Passive - accept without contingency; wait and see
| Typical Risk Categories | Typical Risk Examples
| Cultural Risks | • Stakeholder and customer involvement, commitment or non-involvement
• New or changing processes.
• Customer impact: What is the complexity of customer procedural changes required by the proposed system?
| Skills/Knowledge Risk | • Team skills and experience: Have we done anything like this before?
• Do customers/end users need to be prepared for changes? Will they need training? Ongoing support?
| Schedule Risks | • Staff availability, competing projects or operations work
• Holiday and Vacation Schedules
| Technical Risks | • Is the project oriented to maintenance, enhancement or replacement of an existing system or a completely new system requiring interfaces?
• Will the project require selection and installation of new equipment, hardware or software?
• Will implementation require conversion of data, either in existing systems or in paper form?
• How would you rate the data management discipline exercised in feeder systems? (How clean is the data?)
• How many existing system must the new system interface with?
• How mature is the equipment or hardware/software? How good is the vendor support initially and during the change? Ongoing?
Note on B2: Statement of the risk (See examples below)
Note on C2: Description of the potential impact of the risk on the project (scope, schedule, budget, etc)
Note on F2: Description of actions to prevent or reduce the likelihood of occurence or to reduce the impact
Note on H2: Person responsible for ensuring risk management plan implementation
Note on J2: For easy sorting, track Active or Closed status.

## Lessons
Lessons Learned Worksheet
ID | Date | What worked well? | What was challenging? | Immediation Actions | Longer-term Recommendations | Impact | Process Step | Entered By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
About this Document:
Use this document to capture lessons learned on an ongoing basis. Capture what worked well and should be included in future, similar projects.
Include challenges and recommendations for avoiding or responding to them in future projects.
A quick lessons check-in at the end of each phase can be very helpful. Lessons learned can be leveraged to improve team performance and project quality in the future.
To close the project, Lessons Learned should be complete, reviewed with those responsible for assigning project managers, archived and available to other project managers.
Should you encounter a similar project in the future, you will be thankful for the small amount of effort this exercise takes!

## Close
Project Close Worksheet
Action | Comments & Decisions | Date Completed
Transition
Knowledge transfer, punch list and transition documentation reviewed with all maintenance, operations and support organization(s).
Documentation/training materials updated.
Maintenance/support plans in place.
Maintenance/support organization sign-off and accepts responsibility.
Deliverables/Documentation
Final written acceptance/sign-off of all deliverables with punch list.
Project documentation and deliverables archived.
Financial
Communicate with accounting. Project closed to all charges.
Finalize financials and update portfolio information.
Resource
Team Member reviews completed and forwarded to their managers.
Skills feedback provided to project resource managers.
Contractor staff security badges returned / site access terminated.
Property returned by contractors.
Project Success
Benefits/value follow-up meeting scheduled.
Final Lessons Learned conducted with team.
Formal Close
Report to Sponsor on completion of all close tasks, reviewing delivery performance against plan (e.g., performance against planned cost, schedule, scope with approved changes) and summarized lessons learned. Gather lessons learned feedback from Sponsor perspective.
Lessons Learned documented and distributed to participants & appropriate leadership to improve future projects.
Obtain formal agreement/sign-off to close project. Update portfolio.
Communicate close to all stakeholders along with contact information for support/maintenance.
Celebrate completion, thank and recognize all contributors.
About this Document:
Use this document to ensure all of the items required in your organization are completed before you START your next project.